## Sheet1
Project ID | Project Name | Client Name | Location | Start Date | End Date | Status | Type | Budget (INR) | Actual Cost (INR) | HVAC Type | Cooling (TR) | Heating (kW) | Ventilation | Efficiency | Mech Cost (INR) | Maint/Yr | Power Load (kVA) | Transformer (kVA) | Backup | Lighting | Wiring | Elec Cost (INR) | Energy (kWh/mo) | Water Source | Piping | Pump (HP) | Water Use (L/day) | Sewage | Plumb Cost (INR) | Eng | Tech | Labor | Hrs/Wk | Incidents | Training Hrs | Budget Var (%) | Sched Var (d) | Eff. Score | Satisfaction | Downtime (h/mo) | Compliance | Milestone | Plan Date | Actual Date | Delay | Complete
P001 | Green Heights | EcoBuild | Mumbai | 2023-01-10 | 2023-11-30 | Completed | Residential | 12000000 | 11500000 | VRF | 120 | 45 | Natural | 4 Star | 1800000 | 2 | 150 | 200 | DG | LED | FRLS | 1200000 | 18000 | Municipal | CPVC | 5 | 25000 | STP | 600000 | 3 | 5 | 20 | 48 | 0 | 40 | -4.2 | -10 | 88 | 5 | 2 | 95 | HVAC Commissioning | 2023-09-01 | 2023-09-05 | 4 | Yes
P002 | Tech Park Alpha | BuildCore | Bengaluru | 2022-05-15 | 2023-06-20 | Completed | Commercial | 35000000 | 37000000 | Chiller | 300 | 90 | Mechanical | 5 Star | 4500000 | 3 | 500 | 630 | UPS | LED | XLPE | 3800000 | 55000 | Borewell | GI | 10 | 60000 | STP | 1500000 | 6 | 10 | 50 | 60 | 1 | 80 | 5.7 | 15 | 92 | 4 | 5 | 98 | Electrical Testing | 2023-05-01 | 2023-05-20 | 19 | Yes
P003 | Sunrise Villas | UrbanNest | Pune | 2023-03-01 | 2023-12-15 | In Progress | Residential | 9000000 | 6500000 | Split | 80 | 30 | Natural | 3 Star | 1200000 | 1 | 100 | 160 | DG | CFL | FRLS | 900000 | 12000 | Municipal | PVC | 3 | 18000 | Septic | 400000 | 2 | 3 | 15 | 40 | 0 | 20 | -27.8 | -5 | 75 | 3 | 1 | 85 | Plumbing Layout | 2023-10-01 | 2023-10-01 | 0 | No
P004 | Orion Hospital | MediInfra | Delhi | 2022-08-01 | 2023-08-30 | Completed | Industrial | 48000000 | 46000000 | VRF | 250 | 100 | Mechanical | 5 Star | 6000000 | 4 | 800 | 1000 | DG | LED | XLPE | 5500000 | 85000 | Municipal | CPVC | 15 | 90000 | STP | 2000000 | 8 | 12 | 60 | 72 | 2 | 100 | -4.2 | -2 | 95 | 5 | 3 | 99 | Final Inspection | 2023-07-15 | 2023-07-17 | 2 | Yes
P005 | Skyview Towers | Zenith | Hyderabad | 2023-02-01 | 2023-12-01 | In Progress | Residential | 15000000 | 12000000 | VRF | 150 | 60 | Natural | 4 Star | 2200000 | 2 | 200 | 250 | UPS | LED | FRLS | 1800000 | 25000 | Borewell | CPVC | 6 | 30000 | STP | 700000 | 4 | 6 | 25 | 50 | 0 | 50 | -20 | 0 | 85 | 4 | 2 | 92 | Electrical Layout | 2023-09-01 | 2023-09-01 | 0 | No
P006 | Metro Mall | RetailCorp | Chennai | 2022-11-01 | 2023-10-15 | Completed | Commercial | 28000000 | 29500000 | Chiller | 220 | 85 | Mechanical | 4 Star | 4000000 | 3 | 400 | 500 | DG | LED | XLPE | 3000000 | 48000 | Municipal | GI | 8 | 45000 | STP | 1200000 | 5 | 8 | 40 | 60 | 1 | 70 | 5.4 | 10 | 90 | 4 | 4 | 96 | Fire Safety Check | 2023-08-01 | 2023-08-11 | 10 | Yes
P007 | EcoHub Campus | GreenEdge | Noida | 2023-01-15 | 2023-11-30 | In Progress | Industrial | 50000000 | 39000000 | VRF | 280 | 110 | Mechanical | 5 Star | 5500000 | 4 | 900 | 1250 | Solar | LED | XLPE | 6000000 | 95000 | Borewell | CPVC | 12 | 75000 | STP | 1800000 | 9 | 15 | 70 | 72 | 0 | 120 | -22 | -7 | 97 | 5 | 1 | 99 | HVAC Commissioning | 2023-10-01 | 2023-10-01 | 0 | No
P008 | Azure Heights | EcoSpace | Noida | 2023-03-15 | 2023-11-30 | Completed | Residential | 13000000 | 12500000 | VRF | 150 | 50 | Natural | 4 Star | 2000000 | 2 | 160 | 220 | DG | LED | FRLS | 1300000 | 20000 | Municipal | CPVC | 6 | 28000 | STP | 650000 | 3 | 6 | 22 | 45 | 0 | 45 | -3.8 | -6 | 87 | 4 | 2 | 93 | Final Inspection | 2023-09-10 | 2023-09-12 | 2 | Yes
P009 | Tech Hub | ElevateInfra | Gurgaon | 2023-04-01 | 2023-12-30 | Ongoing | Commercial | 45000000 | 44000000 | Chiller | 550 | 130 | Mechanical | 5 Star | 6000000 | 5 | 650 | 1100 | DG | LED | XLPE | 3500000 | 65000 | Borewell | PVC | 22 | 80000 | STP | 2200000 | 8 | 14 | 55 | 70 | 2 | 100 | -2.2 | 8 | 93 | 5 | 1 | 96 | Energy Audit | 2023-10-25 | — | — | No
P010 | Tranquil Nest | EcoBuild | Indore | 2023-01-10 | 2023-11-30 | Completed | Residential | 9500000 | 9000000 | Split | 110 | 35 | Natural | 3 Star | 1500000 | 2 | 140 | 190 | Inverter | CFL | FRLS | 950000 | 15000 | Municipal | CPVC | 4 | 22000 | Septic | 550000 | 2 | 4 | 16 | 40 | 0 | 28 | -5.3 | -4 | 84 | 4 | 3 | 89 | Water Testing | 2023-09-01 | 2023-09-03 | 2 | Yes
P011 | Corporate Plaza | InfraCore | Mumbai | 2023-02-05 | 2023-11-30 | Completed | Commercial | 32000000 | 31500000 | VRF | 380 | 95 | Mechanical | 4 Star | 4200000 | 3 | 420 | 750 | DG | LED | XLPE | 2700000 | 48000 | Municipal | PVC | 14 | 58000 | STP | 1600000 | 6 | 11 | 38 | 58 | 1 | 75 | -1.6 | -3 | 90 | 5 | 1 | 96 | Fire Drill | 2023-09-10 | 2023-09-11 | 1 | Yes
P012 | Eco Valley | EcoNest | Jaipur | 2023-03-01 | 2023-11-30 | Completed | Residential | 10000000 | 9800000 | Split | 95 | 28 | Natural | 3 Star | 1300000 | 2 | 125 | 170 | Inverter | CFL | FRLS | 900000 | 13000 | Municipal | CPVC | 4 | 19000 | Septic | 480000 | 2 | 4 | 14 | 38 | 0 | 32 | -2 | -2 | 86 | 4 | 2 | 91 | Plumbing Inspection | 2023-09-05 | 2023-09-06 | 1 | Yes
P013 | Metro Mall | BuildMax | Hyderabad | 2023-04-05 | 2023-12-30 | Ongoing | Commercial | 42000000 | 41000000 | Chiller | 500 | 120 | Mechanical | 4 Star | 5500000 | 5 | 600 | 1000 | DG | LED | XLPE | 3200000 | 60000 | Borewell | PVC | 20 | 75000 | STP | 2000000 | 7 | 12 | 50 | 65 | 3 | 90 | -2.4 | 10 | 90 | 4 | 2 | 95 | Lighting Setup | 2023-10-20 | — | — | No
P014 | Skyline Tower | UrbanNest | Delhi | 2023-02-15 | 2023-12-20 | Completed | Commercial | 25000000 | 26000000 | Chiller | 300 | 80 | Mechanical | 5 Star | 3500000 | 3 | 300 | 500 | DG | LED | XLPE | 2200000 | 35000 | Borewell | PVC | 10 | 40000 | STP | 1200000 | 5 | 8 | 30 | 52 | 1 | 60 | 4 | 5 | 92 | 4 | 1 | 98 | Fire Safety Audit | 2023-10-01 | 2023-10-03 | 2 | Yes
P015 | Sunview Villas | NatureBuild | Pune | 2023-03-01 | 2023-11-15 | Completed | Residential | 9000000 | 8800000 | Split | 100 | 30 | Natural | 3 Star | 1400000 | 1 | 120 | 160 | Inverter | CFL | FRLS | 900000 | 14000 | Municipal | CPVC | 4 | 20000 | Septic | 450000 | 2 | 4 | 15 | 40 | 0 | 30 | -2.2 | -5 | 85 | 4 | 3 | 90 | Plumbing Inspection | 2023-09-05 | 2023-09-06 | 1 | Yes
P016 | Tech Park One | InfraCore | Bangalore | 2023-01-10 | 2023-11-30 | Completed | Commercial | 38000000 | 37500000 | VRF | 400 | 100 | Mechanical | 5 Star | 5000000 | 4 | 500 | 800 | DG | LED | XLPE | 3000000 | 50000 | Borewell | PVC | 15 | 60000 | STP | 1800000 | 6 | 10 | 40 | 60 | 2 | 80 | -1.3 | -7 | 95 | 5 | 1 | 99 | Power Onboarding | 2023-09-15 | 2023-09-17 | 2 | Yes
P017 | Harmony Homes | EcoNest | Chennai | 2023-03-20 | 2023-12-25 | Ongoing | Residential | 11000000 | 9500000 | Split | 90 | 25 | Natural | 3 Star | 1600000 | 2 | 130 | 180 | Inverter | CFL | FRLS | 1000000 | 16000 | Municipal | CPVC | 3 | 18000 | Septic | 500000 | 3 | 5 | 18 | 42 | 1 | 35 | -13.6 | 15 | 80 | 3 | 4 | 85 | Plumbing Layout | 2023-10-10 | — | — | No
P018 | Civic Center | InfraTech | Kolkata | 2023-02-10 | 2023-11-30 | Completed | Commercial | 30000000 | 29500000 | VRF | 350 | 90 | Mechanical | 4 Star | 4000000 | 3 | 400 | 700 | DG | LED | XLPE | 2500000 | 45000 | Municipal | PVC | 12 | 55000 | STP | 1500000 | 5 | 9 | 35 | 55 | 1 | 70 | -1.7 | -4 | 91 | 5 | 1 | 97 | Transformer Install | 2023-09-05 | 2023-09-06 | 1 | Yes
P019 | Serene Meadows | GreenBuild | Ahmedabad | 2023-05-01 | 2023-11-30 | Completed | Residential | 8500000 | 8000000 | Split | 80 | 20 | Natural | 3 Star | 1200000 | 1 | 100 | 150 | Inverter | CFL | FRLS | 800000 | 12000 | Municipal | CPVC | 3 | 15000 | Septic | 400000 | 2 | 3 | 12 | 38 | 0 | 25 | -5.9 | -3 | 82 | 4 | 2 | 88 | HVAC Testing | 2023-09-01 | 2023-09-02 | 1 | Yes
P020 | Infinity Tower | UrbanNest | Delhi | 2023-06-01 | 2023-12-31 | Ongoing | Commercial | 28000000 | 27000000 | Chiller | 320 | 85 | Mechanical | 4 Star | 3600000 | 3 | 310 | 520 | DG | LED | XLPE | 2300000 | 36000 | Borewell | PVC | 11 | 42000 | STP | 1300000 | 5 | 7 | 32 | 50 | 1 | 65 | -3.6 | 6 | 89 | 4 | 1 | 94 | Fire Alarm Setup | 2023-10-15 | — | — | No
P021 | Eco Habitat | EcoNest | Lucknow | 2023-03-10 | 2023-11-30 | Completed | Residential | 10500000 | 10000000 | Split | 100 | 30 | Natural | 3 Star | 1450000 | 2 | 135 | 180 | Inverter | CFL | FRLS | 1050000 | 17000 | Municipal | CPVC | 4 | 21000 | Septic | 520000 | 3 | 5 | 17 | 41 | 0 | 33 | -4.8 | -5 | 83 | 4 | 3 | 90 | Water Line Test | 2023-09-08 | 2023-09-09 | 1 | Yes
P022 | Tech Square | InfraCore | Bangalore | 2023-01-05 | 2023-11-30 | Completed | Commercial | 36000000 | 35500000 | VRF | 390 | 98 | Mechanical | 5 Star | 4800000 | 4 | 480 | 780 | DG | LED | XLPE | 2900000 | 52000 | Borewell | PVC | 14 | 59000 | STP | 1750000 | 6 | 10 | 39 | 59 | 2 | 78 | -1.4 | -6 | 94 | 5 | 1 | 98 | Power Backup Test | 2023-09-12 | 2023-09-13 | 1 | Yes
P023 | Blue Horizon | EcoSpace | Surat | 2023-04-15 | 2023-11-30 | Completed | Residential | 11500000 | 11000000 | VRF | 130 | 40 | Natural | 4 Star | 1900000 | 2 | 155 | 210 | DG | LED | FRLS | 1250000 | 19000 | Municipal | CPVC | 5 | 26000 | STP | 620000 | 3 | 6 | 21 | 46 | 0 | 42 | -4.3 | -4 | 86 | 4 | 2 | 92 | Final Plumbing | 2023-09-10 | 2023-09-11 | 1 | Yes
P024 | Smart Plaza | BuildMax | Hyderabad | 2023-05-01 | 2023-12-30 | Ongoing | Commercial | 41000000 | 40000000 | Chiller | 480 | 115 | Mechanical | 4 Star | 5300000 | 5 | 590 | 980 | DG | LED | XLPE | 3100000 | 58000 | Borewell | PVC | 19 | 73000 | STP | 1950000 | 7 | 11 | 49 | 64 | 3 | 88 | -2.4 | 9 | 91 | 4 | 2 | 96 | Lighting Setup | 2023-10-22 | — | — | No
P025 | Peaceful Pines | EcoBuild | Nagpur | 2023-02-10 | 2023-11-30 | Completed | Residential | 9200000 | 8900000 | Split | 105 | 32 | Natural | 3 Star | 1350000 | 2 | 130 | 175 | Inverter | CFL | FRLS | 920000 | 14000 | Municipal | CPVC | 4 | 23000 | Septic | 510000 | 2 | 4 | 15 | 39 | 0 | 30 | -3.3 | -3 | 85 | 4 | 3 | 91 | Water Testing | 2023-09-03 | 2023-09-04 | 1 | Yes
P026 | Vertex Tower | UrbanNest | Delhi | 2023-07-01 | 2023-12-31 | Ongoing | Commercial | 29000000 | 28500000 | Chiller | 310 | 82 | Mechanical | 4 Star | 3400000 | 3 | 305 | 510 | DG | LED | XLPE | 2150000 | 34000 | Borewell | PVC | 10 | 41000 | STP | 1250000 | 5 | 7 | 31 | 51 | 1 | 63 | -1.7 | 4 | 90 | 4 | 1 | 95 | Fire Safety Audit | 2023-10-18 | — | — | No
P027 | Eco Enclave | EcoNest | Patna | 2023-03-05 | 2023-11-30 | Completed | Residential | 10800000 | 10300000 | Split | 98 | 29 | Natural | 3 Star | 1500000 | 2 | 128 | 175 | Inverter | CFL | FRLS | 1000000 | 16000 | Municipal | CPVC | 4 | 20000 | Septic | 540000 | 3 | 5 | 16 | 40 | 0 | 34 | -4.6 | -5 | 84 | 4 | 3 | 89 | Plumbing Inspection | 2023-09-06 | 2023-09-07 | 1 | Yes
P028 | Eco Rise | EcoBuild | Kanpur | 2023-03-12 | 2023-11-30 | Completed | Residential | 12500000 | 12000000 | VRF | 140 | 48 | Natural | 4 Star | 1900000 | 2 | 155 | 210 | DG | LED | FRLS | 1250000 | 19000 | Municipal | CPVC | 5 | 26000 | STP | 620000 | 3 | 6 | 21 | 46 | 0 | 42 | -4 | -5 | 86 | 4 | 2 | 92 | Final Plumbing | 2023-09-10 | 2023-09-11 | 1 | Yes
P029 | Smart Heights | UrbanNest | Delhi | 2023-06-01 | 2023-12-31 | Ongoing | Commercial | 29000000 | 28500000 | Chiller | 310 | 82 | Mechanical | 4 Star | 3400000 | 3 | 305 | 510 | DG | LED | XLPE | 2150000 | 34000 | Borewell | PVC | 10 | 41000 | STP | 1250000 | 5 | 7 | 31 | 51 | 1 | 63 | -1.7 | 4 | 90 | 4 | 1 | 95 | Fire Safety Audit | 2023-10-18 | — | — | No
P030 | Eco Enclave | EcoNest | Patna | 2023-03-05 | 2023-11-30 | Completed | Residential | 10800000 | 10300000 | Split | 98 | 29 | Natural | 3 Star | 1500000 | 2 | 128 | 175 | Inverter | CFL | FRLS | 1000000 | 16000 | Municipal | CPVC | 4 | 20000 | Septic | 540000 | 3 | 5 | 16 | 40 | 0 | 34 | -4.6 | -5 | 84 | 4 | 3 | 89 | Plumbing Inspection | 2023-09-06 | 2023-09-07 | 1 | Yes
P031 | Tech Axis | InfraCore | Bangalore | 2023-01-10 | 2023-11-30 | Completed | Commercial | 39000000 | 38500000 | VRF | 410 | 105 | Mechanical | 5 Star | 5200000 | 4 | 510 | 820 | DG | LED | XLPE | 3100000 | 53000 | Borewell | PVC | 16 | 61000 | STP | 1850000 | 6 | 10 | 41 | 61 | 2 | 82 | -1.3 | -6 | 94 | 5 | 1 | 98 | Power Backup Test | 2023-09-12 | 2023-09-13 | 1 | Yes
P032 | Blue Haven | EcoSpace | Surat | 2023-04-15 | 2023-11-30 | Completed | Residential | 11800000 | 11200000 | VRF | 135 | 42 | Natural | 4 Star | 1850000 | 2 | 150 | 205 | DG | LED | FRLS | 1200000 | 18500 | Municipal | CPVC | 5 | 24000 | STP | 610000 | 3 | 6 | 20 | 45 | 0 | 40 | -5.1 | -4 | 87 | 4 | 2 | 93 | Final Inspection | 2023-09-09 | 2023-09-10 | 1 | Yes
P033 | Smart Square | BuildMax | Hyderabad | 2023-05-01 | 2023-12-30 | Ongoing | Commercial | 41500000 | 40500000 | Chiller | 490 | 118 | Mechanical | 4 Star | 5400000 | 5 | 600 | 990 | DG | LED | XLPE | 3200000 | 59000 | Borewell | PVC | 20 | 74000 | STP | 1980000 | 7 | 11 | 50 | 65 | 3 | 89 | -2.4 | 9 | 91 | 4 | 2 | 96 | Lighting Setup | 2023-10-22 | — | — | No
P034 | Peaceful Grove | EcoBuild | Nagpur | 2023-02-10 | 2023-11-30 | Completed | Residential | 9400000 | 9000000 | Split | 108 | 33 | Natural | 3 Star | 1300000 | 2 | 132 | 178 | Inverter | CFL | FRLS | 900000 | 14500 | Municipal | CPVC | 4 | 22000 | Septic | 500000 | 2 | 4 | 15 | 39 | 0 | 30 | -4.3 | -3 | 85 | 4 | 3 | 91 | Water Testing | 2023-09-03 | 2023-09-04 | 1 | Yes
P035 | Vertex Point | UrbanNest | Delhi | 2023-07-01 | 2023-12-31 | Ongoing | Commercial | 29500000 | 29000000 | Chiller | 315 | 84 | Mechanical | 4 Star | 3500000 | 3 | 310 | 515 | DG | LED | XLPE | 2200000 | 35000 | Borewell | PVC | 11 | 42000 | STP | 1280000 | 5 | 7 | 32 | 52 | 1 | 64 | -1.7 | 4 | 90 | 4 | 1 | 95 | Fire Safety Audit | 2023-10-19 | — | — | No
P036 | Eco Nest | EcoNest | Ranchi | 2023-03-05 | 2023-11-30 | Completed | Residential | 11000000 | 10500000 | Split | 100 | 30 | Natural | 3 Star | 1400000 | 2 | 130 | 180 | Inverter | CFL | FRLS | 1000000 | 16000 | Municipal | CPVC | 4 | 21000 | Septic | 530000 | 3 | 5 | 17 | 41 | 0 | 33 | -4.5 | -5 | 83 | 4 | 3 | 90 | Water Line Test | 2023-09-08 | 2023-09-09 | 1 | Yes
P037 | Tech Sphere | InfraCore | Bangalore | 2023-01-05 | 2023-11-30 | Completed | Commercial | 37000000 | 36500000 | VRF | 385 | 97 | Mechanical | 5 Star | 4700000 | 4 | 470 | 770 | DG | LED | XLPE | 2800000 | 51000 | Borewell | PVC | 14 | 57000 | STP | 1700000 | 6 | 10 | 38 | 58 | 2 | 76 | -1.4 | -6 | 94 | 5 | 1 | 98 | Power Onboarding | 2023-09-11 | 2023-09-12 | 1 | Yes
P038 | Eco Crest | EcoBuild | Varanasi | 2023-03-12 | 2023-11-30 | Completed | Residential | 12200000 | 11800000 | VRF | 145 | 46 | Natural | 4 Star | 1850000 | 2 | 158 | 215 | DG | LED | FRLS | 1220000 | 18800 | Municipal | CPVC | 5 | 25500 | STP | 610000 | 3 | 6 | 21 | 46 | 0 | 42 | -3.3 | -5 | 87 | 4 | 2 | 92 | Final Plumbing | 2023-09-10 | 2023-09-11 | 1 | Yes
P039 | Smart Pinnacle | UrbanNest | Delhi | 2023-06-01 | 2023-12-31 | Ongoing | Commercial | 29500000 | 29000000 | Chiller | 315 | 83 | Mechanical | 4 Star | 3300000 | 3 | 308 | 512 | DG | LED | XLPE | 2200000 | 34500 | Borewell | PVC | 10 | 41500 | STP | 1260000 | 5 | 7 | 31 | 51 | 1 | 63 | -1.7 | 4 | 90 | 4 | 1 | 95 | Fire Safety Audit | 2023-10-18 | — | — | No
P040 | Eco Meadows | EcoNest | Gaya | 2023-03-05 | 2023-11-30 | Completed | Residential | 11200000 | 10700000 | Split | 102 | 31 | Natural | 3 Star | 1450000 | 2 | 129 | 176 | Inverter | CFL | FRLS | 1020000 | 16200 | Municipal | CPVC | 4 | 21500 | Septic | 520000 | 3 | 5 | 17 | 41 | 0 | 33 | -4.5 | -5 | 83 | 4 | 3 | 90 | Water Line Test | 2023-09-08 | 2023-09-09 | 1 | Yes
P041 | Tech Orbit | InfraCore | Bangalore | 2023-01-05 | 2023-11-30 | Completed | Commercial | 37500000 | 37000000 | VRF | 395 | 96 | Mechanical | 5 Star | 4600000 | 4 | 465 | 765 | DG | LED | XLPE | 2750000 | 50500 | Borewell | PVC | 14 | 56500 | STP | 1680000 | 6 | 10 | 38 | 58 | 2 | 76 | -1.3 | -6 | 94 | 5 | 1 | 98 | Power Onboarding | 2023-09-11 | 2023-09-12 | 1 | Yes
P042 | Blue Horizon | EcoSpace | Surat | 2023-04-15 | 2023-11-30 | Completed | Residential | 12000000 | 11500000 | VRF | 138 | 41 | Natural | 4 Star | 1800000 | 2 | 152 | 208 | DG | LED | FRLS | 1180000 | 18300 | Municipal | CPVC | 5 | 24500 | STP | 600000 | 3 | 6 | 20 | 45 | 0 | 40 | -4.2 | -4 | 87 | 4 | 2 | 93 | Final Inspection | 2023-09-09 | 2023-09-10 | 1 | Yes
P043 | Smart Plaza | BuildMax | Hyderabad | 2023-05-01 | 2023-12-30 | Ongoing | Commercial | 42500000 | 41500000 | Chiller | 495 | 119 | Mechanical | 4 Star | 5500000 | 5 | 605 | 995 | DG | LED | XLPE | 3300000 | 59500 | Borewell | PVC | 20 | 74500 | STP | 2000000 | 7 | 11 | 50 | 65 | 3 | 89 | -2.4 | 9 | 91 | 4 | 2 | 96 | Lighting Setup | 2023-10-22 | — | — | No
P044 | Peaceful Pines | EcoBuild | Nagpur | 2023-02-10 | 2023-11-30 | Completed | Residential | 9600000 | 9100000 | Split | 110 | 34 | Natural | 3 Star | 1350000 | 2 | 134 | 180 | Inverter | CFL | FRLS | 930000 | 14800 | Municipal | CPVC | 4 | 22500 | Septic | 510000 | 2 | 4 | 15 | 39 | 0 | 30 | -4.3 | -3 | 85 | 4 | 3 | 91 | Water Testing | 2023-09-03 | 2023-09-04 | 1 | Yes
P045 | Vertex Tower | UrbanNest | Delhi | 2023-07-01 | 2023-12-31 | Ongoing | Commercial | 29200000 | 28700000 | Chiller | 312 | 83 | Mechanical | 4 Star | 3400000 | 3 | 307 | 511 | DG | LED | XLPE | 2180000 | 34200 | Borewell | PVC | 10 | 41200 | STP | 1270000 | 5 | 7 | 31 | 51 | 1 | 63 | -1.7 | 4 | 90 | 4 | 1 | 95 | Fire Safety Audit | 2023-10-19 | — | — | No
P046 | Eco Haven | EcoNest | Raipur | 2023-03-05 | 2023-11-30 | Completed | Residential | 10900000 | 10400000 | Split | 99 | 30 | Natural | 3 Star | 1400000 | 2 | 131 | 179 | Inverter | CFL | FRLS | 1010000 | 16100 | Municipal | CPVC | 4 | 21800 | Septic | 530000 | 3 | 5 | 17 | 41 | 0 | 33 | -4.6 | -5 | 84 | 4 | 3 | 90 | Water Line Test | 2023-09-08 | 2023-09-09 | 1 | Yes
P047 | Tech Sphere | InfraCore | Bangalore | 2023-01-05 | 2023-11-30 | Completed | Commercial | 37200000 | 36700000 | VRF | 388 | 98 | Mechanical | 5 Star | 4750000 | 4 | 472 | 772 | DG | LED | XLPE | 2850000 | 51200 | Borewell | PVC | 14 | 57200 | STP | 1720000 | 6 | 10 | 38 | 58 | 2 | 76 | -1.4 | -6 | 94 | 5 | 1 | 98 | Power Onboarding | 2023-09-11 | 2023-09-12 | 1 | Yes
P048 | Eco Summit | EcoBuild | Amritsar | 2023-03-12 | 2023-11-30 | Completed | Residential | 12600000 | 12100000 | VRF | 142 | 47 | Natural | 4 Star | 1920000 | 2 | 157 | 212 | DG | LED | FRLS | 1240000 | 18600 | Municipal | CPVC | 5 | 25800 | STP | 615000 | 3 | 6 | 21 | 46 | 0 | 42 | -4 | -5 | 86 | 4 | 2 | 92 | Final Plumbing | 2023-09-10 | 2023-09-11 | 1 | Yes
P049 | Smart Ridge | UrbanNest | Delhi | 2023-06-01 | 2023-12-31 | Ongoing | Commercial | 29800000 | 29300000 | Chiller | 318 | 84 | Mechanical | 4 Star | 3450000 | 3 | 309 | 514 | DG | LED | XLPE | 2230000 | 34800 | Borewell | PVC | 10 | 41800 | STP | 1270000 | 5 | 7 | 31 | 51 | 1 | 63 | -1.7 | 4 | 90 | 4 | 1 | 95 | Fire Safety Audit | 2023-10-18 | — | — | No
P050 | Eco Horizon | EcoNest | Agra | 2023-03-05 | 2023-11-30 | Completed | Residential | 11300000 | 10800000 | Split | 104 | 32 | Natural | 3 Star | 1470000 | 2 | 130 | 177 | Inverter | CFL | FRLS | 1030000 | 16300 | Municipal | CPVC | 4 | 21700 | Septic | 525000 | 3 | 5 | 17 | 41 | 0 | 33 | -4.5 | -5 | 83 | 4 | 3 | 90 | Water Line Test | 2023-09-08 | 2023-09-09 | 1 | Yes
P051 | Tech Vertex | InfraCore | Bangalore | 2023-01-05 | 2023-11-30 | Completed | Commercial | 37800000 | 37300000 | VRF | 392 | 97 | Mechanical | 5 Star | 4650000 | 4 | 468 | 768 | DG | LED | XLPE | 2780000 | 50800 | Borewell | PVC | 14 | 56800 | STP | 1690000 | 6 | 10 | 38 | 58 | 2 | 76 | -1.3 | -6 | 94 | 5 | 1 | 98 | Power Onboarding | 2023-09-11 | 2023-09-12 | 1 | Yes
P052 | Blue Nest | EcoSpace | Surat | 2023-04-15 | 2023-11-30 | Completed | Residential | 12100000 | 11600000 | VRF | 136 | 42 | Natural | 4 Star | 1820000 | 2 | 153 | 207 | DG | LED | FRLS | 1190000 | 18400 | Municipal | CPVC | 5 | 24800 | STP | 605000 | 3 | 6 | 20 | 45 | 0 | 40 | -4.2 | -4 | 87 | 4 | 2 | 93 | Final Inspection | 2023-09-09 | 2023-09-10 | 1 | Yes
P053 | Smart Hub | BuildMax | Hyderabad | 2023-05-01 | 2023-12-30 | Ongoing | Commercial | 42800000 | 41800000 | Chiller | 498 | 120 | Mechanical | 4 Star | 5550000 | 5 | 608 | 998 | DG | LED | XLPE | 3350000 | 59800 | Borewell | PVC | 20 | 74800 | STP | 2010000 | 7 | 11 | 50 | 65 | 3 | 89 | -2.4 | 9 | 91 | 4 | 2 | 96 | Lighting Setup | 2023-10-22 | — | — | No
P054 | Peaceful Grove | EcoBuild | Nagpur | 2023-02-10 | 2023-11-30 | Completed | Residential | 9700000 | 9200000 | Split | 112 | 35 | Natural | 3 Star | 1370000 | 2 | 136 | 182 | Inverter | CFL | FRLS | 940000 | 14900 | Municipal | CPVC | 4 | 22800 | Septic | 515000 | 2 | 4 | 15 | 39 | 0 | 30 | -4.3 | -3 | 85 | 4 | 3 | 91 | Water Testing | 2023-09-03 | 2023-09-04 | 1 | Yes
P055 | Vertex Point | UrbanNest | Delhi | 2023-07-01 | 2023-12-31 | Ongoing | Commercial | 29700000 | 29200000 | Chiller | 317 | 85 | Mechanical | 4 Star | 3550000 | 3 | 312 | 517 | DG | LED | XLPE | 2250000 | 35200 | Borewell | PVC | 11 | 42200 | STP | 1290000 | 5 | 7 | 32 | 52 | 1 | 64 | -1.7 | 4 | 90 | 4 | 1 | 95 | Fire Safety Audit | 2023-10-19 | — | — | No
P056 | Eco Nest | EcoNest | Ranchi | 2023-03-05 | 2023-11-30 | Completed | Residential | 11100000 | 10600000 | Split | 101 | 30 | Natural | 3 Star | 1420000 | 2 | 132 | 181 | Inverter | CFL | FRLS | 1020000 | 16100 | Municipal | CPVC | 4 | 21900 | Septic | 535000 | 3 | 5 | 17 | 41 | 0 | 33 | -4.5 | -5 | 83 | 4 | 3 | 90 | Water Line Test | 2023-09-08 | 2023-09-09 | 1 | Yes
P057 | Tech Axis | InfraCore | Bangalore | 2023-01-05 | 2023-11-30 | Completed | Commercial | 37400000 | 36900000 | VRF | 386 | 98 | Mechanical | 5 Star | 4700000 | 4 | 474 | 774 | DG | LED | XLPE | 2800000 | 51400 | Borewell | PVC | 14 | 57400 | STP | 1710000 | 6 | 10 | 38 | 58 | 2 | 76 | -1.4 | -6 | 94 | 5 | 1 | 98 | Power Onboarding | 2023-09-11 | 2023-09-12 | 1 | Yes
P058 | Eco Summit | EcoBuild | Amritsar | 2023-03-12 | 2023-11-30 | Completed | Residential | 12600000 | 12100000 | VRF | 142 | 47 | Natural | 4 Star | 1920000 | 2 | 157 | 212 | DG | LED | FRLS | 1240000 | 18600 | Municipal | CPVC | 5 | 25800 | STP | 615000 | 3 | 6 | 21 | 46 | 0 | 42 | -4 | -5 | 86 | 4 | 2 | 92 | Final Plumbing | 2023-09-10 | 2023-09-11 | 1 | Yes
P059 | Smart Ridge | UrbanNest | Delhi | 2023-06-01 | 2023-12-31 | Ongoing | Commercial | 29800000 | 29300000 | Chiller | 318 | 84 | Mechanical | 4 Star | 3450000 | 3 | 309 | 514 | DG | LED | XLPE | 2230000 | 34800 | Borewell | PVC | 10 | 41800 | STP | 1270000 | 5 | 7 | 31 | 51 | 1 | 63 | -1.7 | 4 | 90 | 4 | 1 | 95 | Fire Safety Audit | 2023-10-18 | — | — | No
P060 | Eco Horizon | EcoNest | Agra | 2023-03-05 | 2023-11-30 | Completed | Residential | 11300000 | 10800000 | Split | 104 | 32 | Natural | 3 Star | 1470000 | 2 | 130 | 177 | Inverter | CFL | FRLS | 1030000 | 16300 | Municipal | CPVC | 4 | 21700 | Septic | 525000 | 3 | 5 | 17 | 41 | 0 | 33 | -4.5 | -5 | 83 | 4 | 3 | 90 | Water Line Test | 2023-09-08 | 2023-09-09 | 1 | Yes
P061 | Tech Vertex | InfraCore | Bangalore | 2023-01-05 | 2023-11-30 | Completed | Commercial | 37800000 | 37300000 | VRF | 392 | 97 | Mechanical | 5 Star | 4650000 | 4 | 468 | 768 | DG | LED | XLPE | 2780000 | 50800 | Borewell | PVC | 14 | 56800 | STP | 1690000 | 6 | 10 | 38 | 58 | 2 | 76 | -1.3 | -6 | 94 | 5 | 1 | 98 | Power Onboarding | 2023-09-11 | 2023-09-12 | 1 | Yes
P062 | Blue Nest | EcoSpace | Surat | 2023-04-15 | 2023-11-30 | Completed | Residential | 12100000 | 11600000 | VRF | 136 | 42 | Natural | 4 Star | 1820000 | 2 | 153 | 207 | DG | LED | FRLS | 1190000 | 18400 | Municipal | CPVC | 5 | 24800 | STP | 605000 | 3 | 6 | 20 | 45 | 0 | 40 | -4.2 | -4 | 87 | 4 | 2 | 93 | Final Inspection | 2023-09-09 | 2023-09-10 | 1 | Yes
P063 | Smart Hub | BuildMax | Hyderabad | 2023-05-01 | 2023-12-30 | Ongoing | Commercial | 42800000 | 41800000 | Chiller | 498 | 120 | Mechanical | 4 Star | 5550000 | 5 | 608 | 998 | DG | LED | XLPE | 3350000 | 59800 | Borewell | PVC | 20 | 74800 | STP | 2010000 | 7 | 11 | 50 | 65 | 3 | 89 | -2.4 | 9 | 91 | 4 | 2 | 96 | Lighting Setup | 2023-10-22 | — | — | No
P064 | Peaceful Grove | EcoBuild | Nagpur | 2023-02-10 | 2023-11-30 | Completed | Residential | 9700000 | 9200000 | Split | 112 | 35 | Natural | 3 Star | 1370000 | 2 | 136 | 182 | Inverter | CFL | FRLS | 940000 | 14900 | Municipal | CPVC | 4 | 22800 | Septic | 515000 | 2 | 4 | 15 | 39 | 0 | 30 | -4.3 | -3 | 85 | 4 | 3 | 91 | Water Testing | 2023-09-03 | 2023-09-04 | 1 | Yes
P065 | Vertex Point | UrbanNest | Delhi | 2023-07-01 | 2023-12-31 | Ongoing | Commercial | 29700000 | 29200000 | Chiller | 317 | 85 | Mechanical | 4 Star | 3550000 | 3 | 312 | 517 | DG | LED | XLPE | 2250000 | 35200 | Borewell | PVC | 11 | 42200 | STP | 1290000 | 5 | 7 | 32 | 52 | 1 | 64 | -1.7 | 4 | 90 | 4 | 1 | 95 | Fire Safety Audit | 2023-10-19 | — | — | No
P066 | Eco Nest | EcoNest | Ranchi | 2023-03-05 | 2023-11-30 | Completed | Residential | 11100000 | 10600000 | Split | 101 | 30 | Natural | 3 Star | 1420000 | 2 | 132 | 181 | Inverter | CFL | FRLS | 1020000 | 16100 | Municipal | CPVC | 4 | 21900 | Septic | 535000 | 3 | 5 | 17 | 41 | 0 | 33 | -4.5 | -5 | 83 | 4 | 3 | 90 | Water Line Test | 2023-09-08 | 2023-09-09 | 1 | Yes
P067 | Tech Axis | InfraCore | Bangalore | 2023-01-05 | 2023-11-30 | Completed | Commercial | 37400000 | 36900000 | VRF | 386 | 98 | Mechanical | 5 Star | 4700000 | 4 | 474 | 774 | DG | LED | XLPE | 2800000 | 51400 | Borewell | PVC | 14 | 57400 | STP | 1710000 | 6 | 10 | 38 | 58 | 2 | 76 | -1.4 | -6 | 94 | 5 | 1 | 98 | Power Onboarding | 2023-09-11 | 2023-09-12 | 1 | Yes
P068 | Eco Crest | EcoBuild | Varanasi | 2023-03-12 | 2023-11-30 | Completed | Residential | 12200000 | 11800000 | VRF | 145 | 46 | Natural | 4 Star | 1850000 | 2 | 158 | 215 | DG | LED | FRLS | 1220000 | 18800 | Municipal | CPVC | 5 | 25500 | STP | 610000 | 3 | 6 | 21 | 46 | 0 | 42 | -3.3 | -5 | 87 | 4 | 2 | 92 | Final Plumbing | 2023-09-10 | 2023-09-11 | 1 | Yes
P069 | Smart Pinnacle | UrbanNest | Delhi | 2023-06-01 | 2023-12-31 | Ongoing | Commercial | 29500000 | 29000000 | Chiller | 315 | 83 | Mechanical | 4 Star | 3300000 | 3 | 308 | 512 | DG | LED | XLPE | 2200000 | 34500 | Borewell | PVC | 10 | 41500 | STP | 1260000 | 5 | 7 | 31 | 51 | 1 | 63 | -1.7 | 4 | 90 | 4 | 1 | 95 | Fire Safety Audit | 2023-10-18 | — | — | No
P070 | Eco Meadows | EcoNest | Gaya | 2023-03-05 | 2023-11-30 | Completed | Residential | 11200000 | 10700000 | Split | 102 | 31 | Natural | 3 Star | 1450000 | 2 | 129 | 176 | Inverter | CFL | FRLS | 1020000 | 16200 | Municipal | CPVC | 4 | 21500 | Septic | 520000 | 3 | 5 | 17 | 41 | 0 | 33 | -4.5 | -5 | 83 | 4 | 3 | 90 | Water Line Test | 2023-09-08 | 2023-09-09 | 1 | Yes
P071 | Tech Orbit | InfraCore | Bangalore | 2023-01-05 | 2023-11-30 | Completed | Commercial | 37500000 | 37000000 | VRF | 395 | 96 | Mechanical | 5 Star | 4600000 | 4 | 465 | 765 | DG | LED | XLPE | 2750000 | 50500 | Borewell | PVC | 14 | 56500 | STP | 1680000 | 6 | 10 | 38 | 58 | 2 | 76 | -1.3 | -6 | 94 | 5 | 1 | 98 | Power Onboarding | 2023-09-11 | 2023-09-12 | 1 | Yes
P072 | Blue Horizon | EcoSpace | Surat | 2023-04-15 | 2023-11-30 | Completed | Residential | 12000000 | 11500000 | VRF | 138 | 41 | Natural | 4 Star | 1800000 | 2 | 152 | 208 | DG | LED | FRLS | 1180000 | 18300 | Municipal | CPVC | 5 | 24500 | STP | 600000 | 3 | 6 | 20 | 45 | 0 | 40 | -4.2 | -4 | 87 | 4 | 2 | 93 | Final Inspection | 2023-09-09 | 2023-09-10 | 1 | Yes
P073 | Smart Plaza | BuildMax | Hyderabad | 2023-05-01 | 2023-12-30 | Ongoing | Commercial | 42500000 | 41500000 | Chiller | 495 | 119 | Mechanical | 4 Star | 5500000 | 5 | 605 | 995 | DG | LED | XLPE | 3300000 | 59500 | Borewell | PVC | 20 | 74500 | STP | 2000000 | 7 | 11 | 50 | 65 | 3 | 89 | -2.4 | 9 | 91 | 4 | 2 | 96 | Lighting Setup | 2023-10-22 | — | — | No
P074 | Peaceful Pines | EcoBuild | Nagpur | 2023-02-10 | 2023-11-30 | Completed | Residential | 9600000 | 9100000 | Split | 110 | 34 | Natural | 3 Star | 1350000 | 2 | 134 | 180 | Inverter | CFL | FRLS | 930000 | 14800 | Municipal | CPVC | 4 | 22500 | Septic | 510000 | 2 | 4 | 15 | 39 | 0 | 30 | -4.3 | -3 | 85 | 4 | 3 | 91 | Water Testing | 2023-09-03 | 2023-09-04 | 1 | Yes
P075 | Vertex Tower | UrbanNest | Delhi | 2023-07-01 | 2023-12-31 | Ongoing | Commercial | 29200000 | 28700000 | Chiller | 312 | 83 | Mechanical | 4 Star | 3400000 | 3 | 307 | 511 | DG | LED | XLPE | 2180000 | 34200 | Borewell | PVC | 10 | 41200 | STP | 1270000 | 5 | 7 | 31 | 51 | 1 | 63 | -1.7 | 4 | 90 | 4 | 1 | 95 | Fire Safety Audit | 2023-10-19 | — | — | No
P076 | Eco Haven | EcoNest | Raipur | 2023-03-05 | 2023-11-30 | Completed | Residential | 10900000 | 10400000 | Split | 99 | 30 | Natural | 3 Star | 1400000 | 2 | 131 | 179 | Inverter | CFL | FRLS | 1010000 | 16100 | Municipal | CPVC | 4 | 21800 | Septic | 530000 | 3 | 5 | 17 | 41 | 0 | 33 | -4.6 | -5 | 84 | 4 | 3 | 90 | Water Line Test | 2023-09-08 | 2023-09-09 | 1 | Yes
P077 | Tech Sphere | InfraCore | Bangalore | 2023-01-05 | 2023-11-30 | Completed | Commercial | 37200000 | 36700000 | VRF | 388 | 98 | Mechanical | 5 Star | 4750000 | 4 | 472 | 772 | DG | LED | XLPE | 2850000 | 51200 | Borewell | PVC | 14 | 57200 | STP | 1720000 | 6 | 10 | 38 | 58 | 2 | 76 | -1.4 | -6 | 94 | 5 | 1 | 98 | Power Onboarding | 2023-09-11 | 2023-09-12 | 1 | Yes
P078 | Eco Rise | EcoBuild | Kanpur | 2023-03-12 | 2023-11-30 | Completed | Residential | 12500000 | 12000000 | VRF | 140 | 48 | Natural | 4 Star | 1900000 | 2 | 155 | 210 | DG | LED | FRLS | 1250000 | 19000 | Municipal | CPVC | 5 | 26000 | STP | 620000 | 3 | 6 | 21 | 46 | 0 | 42 | -4 | -5 | 86 | 4 | 2 | 92 | Final Plumbing | 2023-09-10 | 2023-09-11 | 1 | Yes
P079 | Smart Heights | UrbanNest | Delhi | 2023-06-01 | 2023-12-31 | Ongoing | Commercial | 29000000 | 28500000 | Chiller | 310 | 82 | Mechanical | 4 Star | 3400000 | 3 | 305 | 510 | DG | LED | XLPE | 2150000 | 34000 | Borewell | PVC | 10 | 41000 | STP | 1250000 | 5 | 7 | 31 | 51 | 1 | 63 | -1.7 | 4 | 90 | 4 | 1 | 95 | Fire Safety Audit | 2023-10-18 | — | — | No
P080 | Eco Pavilion | EcoBuild | Indore | 2023-03-10 | 2023-11-30 | Completed | Residential | 12400000 | 11900000 | VRF | 144 | 46 | Natural | 4 Star | 1840000 | 2 | 156 | 214 | DG | LED | FRLS | 1230000 | 18700 | Municipal | CPVC | 5 | 25600 | STP | 612000 | 3 | 6 | 21 | 46 | 0 | 42 | -4 | -5 | 86 | 4 | 2 | 92 | Final Plumbing | 2023-09-10 | 2023-09-11 | 1 | Yes
P081 | Smart Crest | UrbanNest | Delhi | 2023-06-01 | 2023-12-31 | Ongoing | Commercial | 29600000 | 29100000 | Chiller | 316 | 84 | Mechanical | 4 Star | 3420000 | 3 | 310 | 513 | DG | LED | XLPE | 2210000 | 34600 | Borewell | PVC | 10 | 41600 | STP | 1265000 | 5 | 7 | 31 | 51 | 1 | 63 | -1.7 | 4 | 90 | 4 | 1 | 95 | Fire Safety Audit | 2023-10-18 | — | — | No
P082 | Eco Grove | EcoNest | Varanasi | 2023-03-05 | 2023-11-30 | Completed | Residential | 11400000 | 10900000 | Split | 103 | 31 | Natural | 3 Star | 1460000 | 2 | 128 | 175 | Inverter | CFL | FRLS | 1025000 | 16250 | Municipal | CPVC | 4 | 21600 | Septic | 522000 | 3 | 5 | 17 | 41 | 0 | 33 | -4.5 | -5 | 83 | 4 | 3 | 90 | Water Line Test | 2023-09-08 | 2023-09-09 | 1 | Yes
P083 | Tech Core | InfraCore | Bangalore | 2023-01-05 | 2023-11-30 | Completed | Commercial | 37600000 | 37100000 | VRF | 393 | 97 | Mechanical | 5 Star | 4620000 | 4 | 466 | 766 | DG | LED | XLPE | 2760000 | 50600 | Borewell | PVC | 14 | 56600 | STP | 1685000 | 6 | 10 | 38 | 58 | 2 | 76 | -1.3 | -6 | 94 | 5 | 1 | 98 | Power Onboarding | 2023-09-11 | 2023-09-12 | 1 | Yes
P084 | Blue Haven | EcoSpace | Surat | 2023-04-15 | 2023-11-30 | Completed | Residential | 12200000 | 11700000 | VRF | 137 | 42 | Natural | 4 Star | 1810000 | 2 | 154 | 206 | DG | LED | FRLS | 1185000 | 18350 | Municipal | CPVC | 5 | 24700 | STP | 607000 | 3 | 6 | 20 | 45 | 0 | 40 | -4.2 | -4 | 87 | 4 | 2 | 93 | Final Inspection | 2023-09-09 | 2023-09-10 | 1 | Yes
P085 | Smart Square | BuildMax | Hyderabad | 2023-05-01 | 2023-12-30 | Ongoing | Commercial | 42600000 | 41600000 | Chiller | 496 | 120 | Mechanical | 4 Star | 5520000 | 5 | 606 | 996 | DG | LED | XLPE | 3320000 | 59600 | Borewell | PVC | 20 | 74600 | STP | 2005000 | 7 | 11 | 50 | 65 | 3 | 89 | -2.4 | 9 | 91 | 4 | 2 | 96 | Lighting Setup | 2023-10-22 | — | — | No
P086 | Peaceful Heights | EcoBuild | Nagpur | 2023-02-10 | 2023-11-30 | Completed | Residential | 9800000 | 9300000 | Split | 113 | 35 | Natural | 3 Star | 1380000 | 2 | 137 | 183 | Inverter | CFL | FRLS | 950000 | 15000 | Municipal | CPVC | 4 | 22900 | Septic | 518000 | 2 | 4 | 15 | 39 | 0 | 30 | -4.3 | -3 | 85 | 4 | 3 | 91 | Water Testing | 2023-09-03 | 2023-09-04 | 1 | Yes
P087 | Vertex Hub | UrbanNest | Delhi | 2023-07-01 | 2023-12-31 | Ongoing | Commercial | 29900000 | 29400000 | Chiller | 319 | 85 | Mechanical | 4 Star | 3560000 | 3 | 313 | 518 | DG | LED | XLPE | 2260000 | 35300 | Borewell | PVC | 11 | 42300 | STP | 1295000 | 5 | 7 | 32 | 52 | 1 | 64 | -1.7 | 4 | 90 | 4 | 1 | 95 | Fire Safety Audit | 2023-10-19 | — | — | No
P088 | Eco Nest | EcoNest | Ranchi | 2023-03-05 | 2023-11-30 | Completed | Residential | 11200000 | 10700000 | Split | 102 | 30 | Natural | 3 Star | 1430000 | 2 | 133 | 182 | Inverter | CFL | FRLS | 1030000 | 16200 | Municipal | CPVC | 4 | 22000 | Septic | 532000 | 3 | 5 | 17 | 41 | 0 | 33 | -4.5 | -5 | 83 | 4 | 3 | 90 | Water Line Test | 2023-09-08 | 2023-09-09 | 1 | Yes
P089 | Tech Axis | InfraCore | Bangalore | 2023-01-05 | 2023-11-30 | Completed | Commercial | 37300000 | 36800000 | VRF | 387 | 98 | Mechanical | 5 Star | 4720000 | 4 | 473 | 773 | DG | LED | XLPE | 2820000 | 51300 | Borewell | PVC | 14 | 57300 | STP | 1715000 | 6 | 10 | 38 | 58 | 2 | 76 | -1.4 | -6 | 94 | 5 | 1 | 98 | Power Onboarding | 2023-09-11 | 2023-09-12 | 1 | Yes
P090 | Eco Pavilion | EcoBuild | Indore | 2023-03-10 | 2023-11-30 | Completed | Residential | 12300000 | 11800000 | VRF | 143 | 46 | Natural | 4 Star | 1830000 | 2 | 157 | 213 | DG | LED | FRLS | 1225000 | 18750 | Municipal | CPVC | 5 | 25700 | STP | 611000 | 3 | 6 | 21 | 46 | 0 | 42 | -4 | -5 | 86 | 4 | 2 | 92 | Final Plumbing | 2023-09-10 | 2023-09-11 | 1 | Yes
P091 | Smart Crest | UrbanNest | Delhi | 2023-06-01 | 2023-12-31 | Ongoing | Commercial | 29700000 | 29200000 | Chiller | 317 | 84 | Mechanical | 4 Star | 3430000 | 3 | 311 | 515 | DG | LED | XLPE | 2220000 | 34700 | Borewell | PVC | 10 | 41700 | STP | 1268000 | 5 | 7 | 31 | 51 | 1 | 63 | -1.7 | 4 | 90 | 4 | 1 | 95 | Fire Safety Audit | 2023-10-18 | — | — | No
P092 | Eco Grove | EcoNest | Varanasi | 2023-03-05 | 2023-11-30 | Completed | Residential | 11500000 | 11000000 | Split | 105 | 31 | Natural | 3 Star | 1480000 | 2 | 129 | 176 | Inverter | CFL | FRLS | 1040000 | 16300 | Municipal | CPVC | 4 | 21700 | Septic | 528000 | 3 | 5 | 17 | 41 | 0 | 33 | -4.5 | -5 | 83 | 4 | 3 | 90 | Water Line Test
P093 | Eco Haven | EcoBuild | Dehradun | 2023-03-10 | 2023-11-30 | Completed | Residential | 12200000 | 12000000 | VRF | 140 | 45 | Natural | 4 Star | 1800000 | 2 | 150 | 200 | DG | LED | FRLS | 1200000 | 18000 | Municipal | CPVC | 5 | 25000 | STP | 600000 | 3 | 5 | 20 | 48 | 0 | 40 | -4.2 | -10 | 88 | 5 | 2 | 95 | HVAC Commissioning | 2023-09-01 | 2023-09-05 | 4 | Yes
P094 | Smart Point | UrbanNest | Delhi | 2023-06-01 | 2023-12-31 | Ongoing | Commercial | 42600000 | 30000000 | Chiller | 320 | 85 | Mechanical | 4 Star | 3500000 | 3 | 315 | 520 | DG | LED | XLPE | 2300000 | 35000 | Borewell | PVC | 10 | 42000 | STP | 1300000 | 5 | 7 | 32 | 52 | 1 | 64 | -1.7 | 4 | 90 | 4 | 1 | 95 | Fire Safety Audit | 2023-10-18 | — | — | No
P095 | Eco Retreat | EcoNest | Shimla | 2023-03-05 | 2023-11-30 | Completed | Residential | 9800000 | 11000000 | Split | 100 | 30 | Natural | 3 Star | 1400000 | 2 | 130 | 180 | Inverter | CFL | FRLS | 1000000 | 16000 | Municipal | CPVC | 4 | 21000 | Septic | 530000 | 3 | 5 | 17 | 41 | 0 | 33 | -4.5 | -5 | 83 | 4 | 3 | 90 | Water Line Test | 2023-09-08 | 2023-09-09 | 1 | Yes
P096 | Tech Central | InfraCore | Bangalore | 2023-01-05 | 2023-11-30 | Completed | Commercial | 29900000 | 38000000 | VRF | 400 | 100 | Mechanical | 5 Star | 5000000 | 4 | 500 | 800 | DG | LED | XLPE | 3000000 | 50000 | Borewell | PVC | 15 | 60000 | STP | 1800000 | 6 | 10 | 40 | 60 | 2 | 80 | -1.3 | -7 | 95 | 5 | 1 | 99 | Power Onboarding | 2023-09-15 | 2023-09-17 | 2 | Yes
P097 | Blue Horizon | EcoSpace | Surat | 2023-04-15 | 2023-11-30 | Completed | Residential | 11200000 | 11800000 | VRF | 135 | 42 | Natural | 4 Star | 1850000 | 2 | 150 | 205 | DG | LED | FRLS | 1200000 | 18500 | Municipal | CPVC | 5 | 24000 | STP | 610000 | 3 | 6 | 20 | 45 | 0 | 40 | -5.1 | -4 | 87 | 4 | 2 | 93 | Final Inspection | 2023-09-10 | 2023-09-11 | 1 | Yes
P098 | Smart Hub | BuildMax | Hyderabad | 2023-05-01 | 2023-12-30 | Ongoing | Commercial | 37300000 | 43000000 | Chiller | 500 | 120 | Mechanical | 4 Star | 5600000 | 5 | 610 | 1000 | DG | LED | XLPE | 3400000 | 60000 | Borewell | PVC | 20 | 75000 | STP | 2020000 | 7 | 11 | 50 | 65 | 3 | 90 | -2.4 | 9 | 91 | 4 | 2 | 96 | Lighting Setup | 2023-10-22 | — | — | No
P099 | Peaceful Grove | EcoBuild | Nagpur | 2023-02-10 | 2023-11-30 | Completed | Residential | 12300000 | 9900000 | Split | 115 | 36 | Natural | 3 Star | 1400000 | 2 | 138 | 185 | Inverter | CFL | FRLS | 960000 | 15000 | Municipal | CPVC | 4 | 23000 | Septic | 520000 | 2 | 4 | 15 | 39 | 0 | 30 | -4.3 | -3 | 85 | 4 | 3 | 91 | Water Testing | 2023-09-04 | 2023-09-05 | 1 | Yes
P100 | Vertex Plaza | UrbanNest | Delhi | 2023-07-01 | 2023-12-31 | Ongoing | Commercial | 29700000 | 30200000 | Chiller | 322 | 86 | Mechanical | 4 Star | 3600000 | 3 | 318 | 522 | DG | LED | XLPE | 2320000 | 35500 | Borewell | PVC | 11 | 42500 | STP | 1310000 | 5 | 7 | 32 | 52 | 1 | 64 | -1.7 | 4 | 90 | 4 | 1 | 95 | Fire Safety Audit | 2023-10-19 | — | — | No
P101 | Eco Nest | EcoNest | Ranchi | 2023-03-05 | 2023-11-30 | Completed | Residential | 11500000 | 11300000 | Split | 103 | 30 | Natural | 3 Star | 1450000 | 2 | 134 | 183 | Inverter | CFL | FRLS | 1040000 | 16200 | Municipal | CPVC | 4 | 22000 | Septic | 540000 | 3 | 5 | 17 | 41 | 0 | 33 | -4.5 | -5 | 83 | 4 | 3 | 90 | Water Line Test | 2023-09-09 | 2023-09-10 | 1 | Yes
P102 | Tech Axis | InfraCore | Bangalore | 2023-01-05 | 2023-11-30 | Completed | Commercial | 12200000 | 37500000 | VRF | 390 | 98 | Mechanical | 5 Star | 4700000 | 4 | 475 | 775 | DG | LED | XLPE | 2850000 | 51500 | Borewell | PVC | 14 | 57500 | STP | 1720000 | 6 | 10 | 38 | 58 | 2 | 76 | -1.4 | -6 | 94 | 5 | 1 | 98 | Power Onboarding | 2023-09-12 | 2023-09-13 | 1 | Yes